PIPAVAV RAILWAY CORPN. LTD.

CIN U45200DL2000PLC151199

As part of its Corporate Social Responsibility (CSR), Pipavav Railway Corporation Limited completed and handed-over 100 bio-toilets to the residents of Raska Village, Limbdi District, Gujarat.  The Project commenced in December 2015 and completed in the 1st week of August 2016.  The project was executed through NGO - Community Friendly Movement.

Sr. Manager (HR & Admin.)

9th August 2016